## Q&A_15130132_NguyenTanNhut
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | Content management | HKS_ScreenDesign_II. Quan ly noi dung B1 Tim kiem noi dung de duyet.xlsx | 1.0 | [Sort by time] feature | A system didn't sort topics by the time the topics were uploaded | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:Something wrong with the sort feature Toan 10-12-2018:the problem will be fixed soon | Open | Developer team | High | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018
2 | Content management | HKS_ScreenDesign_II. Quan ly noi dung B1 Tim kiem noi dung de duyet.xlsx | 1.0 | [Searching] feature | A [searching] feature didn't work correctly if I type upper-case word in the field | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:The field didn't accept upper-case word,please check Toan 10-12-2018:the problem will be fixed soon | Open | Developer team | Medium | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018
3 | Content management | HKS_ScreenDesign_II. Quan ly noi dung B2 B3 Xem chi tiet noi dung Sua Duyet.xlsx | 1.0 | Upload avatar | The [upload] field can still accept a file that not a image file,for example:txt file,doc file,xlsx file,please check | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:The field didn't have file type filter Toan 10-12-2018:The file filter was added | Finished | Developer team | Medium | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018 | 2018-10-12
4 | Content management | HKS_ScreenDesign_II. Quan ly noi dung C1 Quan ly tin tuc.xlsx | 1.0 | Number of content displayed for each page | There should be 10 content per page,but it only have 7 content for each page | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:The number of content per page is totally wrong Toan 10-12-2018:The problem with be fixed soon | Open | Developer team | Low | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018
5 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi A1 A2 Dang ky.xlsx | 1.0 | [First name],[Last name] and [email] field | All three fields don't have max length validation,and [required] attribute | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:Developer forget to add it Toan 10-12-2018:The problem was fixed | Finished | Developer team | Medium | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018 | 2018-10-12
6 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi B1 B2 Dang nhap.xlsx | 1.0 | [Email field] and [password] field | All two field don't have [required] attribute,and [password] field doesn't hide my text | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:Some attributes need to be added Toan 10-12-2018:The problem was fixed | Finished | Developer team | Medium | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018 | 2018-11-12
7 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi C2 Doi mat khau.xlsx | 1.0 | [Current password] field | The field doesn't hide current user password,the password can be seen by anyone,please fix quickly | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:This error is very dangerous Toan 10-12-2018:The problem was fixed | Finished | Developer team | High | 1.0.1 | Nhan | 2018-08-12 | 14/12/2018 | 2018-11-12
8 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi C2 Doi mat khau.xlsx | 1.0 | [New password] and [Confirm password] field | The fields doesn't check if whether the new password match with the text in confirm password field | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:Currenly user can't change their password because of this Toan 10-12-2018:The problem will be fixed soon | Open | Developer team | High | 1.0.1 | Nhan | 2018-08-12 | 14/12/2018
9 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi D4 Xem noi dung phan hoi Comment.xlsx | 1.0 | Comment's content length | A comment's content doesn't have maximum length,I can type over 100000 word and it still accept | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:This can break UI of the page Toan 10-12-2018:The problem was fixed | Finished | Developer team | Low | 1.0.1 | Nhan | 2018-08-12 | 14/12/2018 | 2018-11-12
10 | Content management | HKS_ScreenDesign_II. Quan ly noi dung C3 Quan ly comment.xlsx | 1.0 | [Searching] feature | [Searching] feature should have a button that filter what field in a table they want to search | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:This can make searching easier for user Toan 10-12-2018:This problem is under discussion | Open | Developer team | Medium | 1.0.1 | Nhan | 2018-08-12 | 14/12/2018
11 | Content management | HKS_ScreenDesign_II. Quan ly noi dung B2 Xem chi tiet noi dung.xlsx | 1.0 | Image | Carousel image size is a little bit larger than the one in the design plan,please check it | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:width and height of the image is wrong Toan 10-12-2018:This problem was fixed | Finished | Developer team | Low | 1.1.1 | Nhan | 2018-08-12 | 14/12/2018 | 2018-11-12
12 | Content management | HKS_ScreenDesign_II. Quan ly noi dung B2 B3 Xem chi tiet noi dung Sua Duyet.xlsx | 1.0 | [Content] field | [Content] field doesn't have [add image] button,only text,please check it | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:developer forget to add the button Toan 10-12-2018:The button was added | Finished | Developer team | Medium | 1.1.1 | Tuong | 2018-08-12 | 14/12/2018 | 2018-11-12
13 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi D3 Theo doi so lieu khai thac thu vien.xlsx | 1.0 | Export excel | Exported excel file's content doesn't display correctly,please confirm and check it again | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:There are some problems with excel export feature Toan 10-12-2018:The problem will be fixed soon | Open | Developer team | Medium | 1.0.1 | Tuong | 2018-08-12 | 14/12/2018
14 | End User | HKS_ScreenDesign_V. Nguoi dung cuoi B1 B2 Dang nhap.xlsx | 1.0 | [Remember me] feature | A [remember me] option doesn't save previous information,please check it | Nhut 8-12-2018:Please assign to development team Toan 10-12-2018:The problem was fixed | Finished | Developer team | Low | 1.1.1 | Tuong | 2018-08-12 | 14/12/2018 | 2018-11-12
15 | Content management | HKS_ScreenDesign_V. Nguoi dung cuoi C3 Phuc hoi mat khau.xlsx | 1.0 | [Password] field and [confirm password] field | The [password] field doesn't hide a text,and a [confirm password] field doesn't check whether the text in this field match with the text in [password] field | Nhut 8-12-2018:Please assign to development team Thuy 8-12-2018:Please fix it quickly Toan 10-12-2018:The problem will be fixed soon | Open | Developer team | High | 1.1.1 | Tuong | 2018-08-12 | 14/12/2018

## Q&A_15130192_NguyenThiThuy
ID: | 15130192
Name | NguyenThiThuy
Class | DH15DTB
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | Display General Information | HKS_High level requirement_20181126.xlsx | 0.3 | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | Rename "Được tải nhiều nhất" to "Tìm kiếm gần đây" and a select tag should includes [Hôm nay], [Tuần này], [Tháng này], [Nhiều lượt thích], [Nhiều lượt tải] fields. We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
2 | Display General Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | In case of special characters will reset the database of the system. If the user enters that special character into the search box, does the system prevent or show errors? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
3 | Display General Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | When a user enters the search box with a maximum length limit for input characters, does the system distinguish between uppercase or lowercase? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
4 | Display General Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | The list box of items must be aligned to create a comfortable view. We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
5 | Display General Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | After performing the search, an icon next to will be displayed to delete all the text entered in the search box and to reset the content display page. We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
6 | Display General Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | Should you limit the number of items in your pagination and maximize the number of items on an expansion page? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
7 | Display General Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A1 Tim kiem Xem thong tin chung | Should you limit the file size on the system? If the file uploaded by the user is larger than the allowable size, the system will display the error, I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
8 | Details Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A2 Xem thong tin chi tiet | The [Download] button needs to be red in order to avoid misleading the download disable. We assume that it is necessary and should be edited? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
9 | Details Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A2 Xem thong tin chi tiet | When the user click the [like] button, the system should switch to the [liked] state and change the color instead of the successful like message.We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
10 | Details Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A2 Xem thong tin chi tiet | When you click the [Share] button, users can sharing through social networks or display links for users to copy. I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
11 | Details Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A2 Xem thong tin chi tiet | The size of the images displayed must be equal right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
12 | Details Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A2 Xem thong tin chi tiet | You need to create a slider with the picture on the radio input tag for the user to click on the picture [Image slider]. I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
13 | Details Information | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A2 Xem thong tin chi tiet | Create a select tag that includes the [Delete] and [Edit] fields for the user to delete and edit the comment they just made.We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
14 | Manage Attach Item In Library | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A3 Xem file dinh kem cua item trong thu vien | Users can view attachments in the library as: pdf, .gif, image, video uploaded or embedded from youtuble. I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
15 | Manage Attach Item In Library | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A3 Xem file dinh kem cua item trong thu vien | Use the icon instead of [download file] in the right corner of the screen and add the ability to upload to google driver, sharing through social networks. We assume that it is necessary and it will be added? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
16 | Manage Attach Item In Library | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung A3 Xem file dinh kem cua item trong thu vien | Use the [scrollbar] to limit the list of files displayed on the screen. We assume that it is necessary and it will be added? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
17 | Display Scientific Writing | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung B1 Search va filter theo thoi gian | The name of the author and the date of the event in the calendar should be in bold. We assume that it is necessary and it will be added? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
18 | Display Scientific Writing | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung B1 Search va filter theo thoi gian | Collapse the [view], [like], [comment] fields into the icons in the right corner of the article and use "pagination" to paginate the posts.We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
19 | Event for user | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_VII. Hien thi noi dung D1 Hien thi su kien | For datepicker, the user entered the date in the [To] field smaller than the date in the [From] field, would the system show an error? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
20 | Find Job | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_IX.Tim viec A1 Liet ke thong tin xin viec | Add [STT] columns to manage the number of candidate records. We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
21 | Find Job | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_IX.Tim viec A3 Dang thong tin tuyen dung | It should be added to the [Xem trước] button for users to review information before posting. We assume that it is necessary and will be add? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
22 | Find Job | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_IX.Tim viec B1 Liet ke thong tin tuyen dung | Change the [Tìm] button to the icon. We assume that it is necessary and should be edited? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
23 | Find Job | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_IX.Tim viec B1 Z Liet ke nha tuyen dung da xem ho so cua ung vien | Profile viewing time must be displayed in full: dd / mm / yyyy HH: SS. We assume that it is necessary and will be add? Please confirm |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
24 | Chat with technician | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_XI. Ho tro ky thuat A1 Web chat voi nguoi ho tro ky thuat | Attached files will be limited in size and limited to malicious files. I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
25 | Chat with technician | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_XI. Ho tro ky thuat A1 Web chat voi nguoi ho tro ky thuat | Should I add the status and time of viewing messages under each message? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
26 | Chat with technician | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_XI. Ho tro ky thuat A2 PhoneApp chát với nhân viên kỹ thuật | Unlimited message content? I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018
27 | Chat with technician | HKS_High level requirement_20181126.xlsx |  | HKS_ScreenDesign_XI. Ho tro ky thuat A2 PhoneApp chát với nhân viên kỹ thuật | Only if the support person is online so the user can call or video calls. I understand this right? Please confirm. |  | Open |  | High |  | Nguyen Thuy | 11/12/2018

## Q&A_15130121_HoTrongNhan
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | Contact us | HKS_ScreenDesign_IV. Lien he gop y A1 A3 Quan ly thong tin lien he gop y | 1.0 | [Search] field | [Search] field not recognize upper case | Nhut 10.12.2018: Assign to developer team Thuy 10.12.2018: Please fix quickly Toan 10.12.2018: On my way | Open |  | Low | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14
2 | Contact us | HKS_ScreenDesign_IV. Lien he gop y A1 A3 Quan ly thong tin lien he gop y | 1.0 | User image | The image of the user not showing correctly | Nhut 10.12.2018: Assign to developer team Thuy 10.12.2018: Image got error while the user comment Toan 10.12.2018: fixed, ready to use again | Finished |  | Low | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16
3 | Contact us | HKS_ScreenDesign_IV. Lien he gop y A1 A3 Quan ly thong tin lien he gop y | 1.0 | [User comment] field | [Comment] field doesn’t have limit character, can type exceed 9999+ char | Nhut 10.12.2018: Assign to developer team Thuy 10.12.2018: Put a limit to the comment please Toan 10.12.2018: Done | Finished |  | Low | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16
4 | Contact us | HKS_ScreenDesign_IV. Lien he gop y A2 A4 Quan ly phan hoi lien he gop y | 1.0 | [Attach File] Field | Cant click to the file to preview it after attached | Nhut 10.12.2018: Assign to developer team Thuy 10.12.2018: Fix it soon please, so inconvenient Toan 10.12.2018: Done | Finished |  | Low | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16
5 | Internal users | HKS_ScreenDesign_VI. Nguoi dung noi bo A1 A2 A3 A4 Quan ly tin su kien (CRUDE) | 1.0 | Set [event] date | Can choose the end event day before started day | Nhut 10.12.2018: Assign to developer team Nhan 10.12.2018: Must fix now Toan 10.12.2018: Done | Finished |  | Medium | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16
6 | Internal users | HKS_ScreenDesign_VI. Nguoi dung noi bo A1 A2 A3 A4 Quan ly tin su kien (CRUDE) | 1.0 | Create [event] | Can duplicated event started day when create event | Nhut 10.12.2018: Assign to developer team Nhan 10.12.2018: This is so important, have to be fixed quickly Toan 10.12.2018: Done | Finished |  | High | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16
7 | Internal users | HKS_ScreenDesign_VI. Nguoi dung noi bo B1 B2 B3 B4 Quan ly tin tuc (CRUDE) | 1.0 | Export excel | Exported excel file not in correct format, file unable to read | Nhut 10.12.2018: Assign to developer team Nhan 10.12.2018: Excel exported files cant read Toan 10.12.2018: Fix it later | Open |  | Medium | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14
8 | Internal users | HKS_ScreenDesign_VI. Nguoi dung noi bo B1 B2 B3 B4 Quan ly tin tuc (CRUDE) | 1.0 | Print service | Cant connect to the printer | Nhut 10.12.2018: Assign to developer team Nhan 10.12.2018: The connection between program and printer got interrupt. Fix it quickly Toan 10.12.2018: Will be fix soon | Open |  | High | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14
9 | Advanced verification | HKS_ScreenDesign_XII. Xac thuc nang cao A1 A2 A3 Dang nhap bang khuon mat | 1.0 | Face recognization | Cant recognize face | Nhut 10.12.2018: Assign to developer team Nhan 10.12.2018: Face cant be recognized correctly Toan 10.12.2018: Fixed | Finished |  | High | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16
10 | Advanced verification | HKS_ScreenDesign_XII. Xac thuc nang cao A1 A2 A3 Dang nhap bang khuon mat | 1.0 | [Register] Form | All field in the form doesn’t have right validation | Nhut 10.12.2018: Assign to developer team Nhan 10.12.2018: All the section in the form need to be fixed Toan 10.12.2018: Fixed | Finished |  | Medium | 1.0.1 | Hoai Xuan | 2018-12-10 | 2018-12-14 | 2018-12-16

## Q&A_15130198_NguyenDuyToan
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | System management | HKS_High level requirement_20181126.xlsx |  | Add groups | On Add Groups screen have not yet had [Cancel] button (On AM folder). I assume that it is necessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to design committee John 11-12-2018 (on behalf of design committee): For Add Groups screen, "Cancel" button is necessary. Hien 11-12-2018 It had been completed. | Complete |  | Cao | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
2 | System management | HKS_High level requirement_20181126.xlsx |  | Add groups | The maximum number of characters that can be entered into a [Group Name] text field are 50 characters. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will add it later Hien 11-12-2018 It had been completed. | Complete |  | Cao | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
3 | System management | HKS_High level requirement_20181126.xlsx |  | Add groups | The maximum number of groups that can be added at the same time are 10 groups. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Cao | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
4 | System management | HKS_High level requirement_20181126.xlsx |  | Add groups | The system should display a list of new groups on the screen if they are added successfully or display an error message if they add to the failure. Please confirm. | Nhan 11-12-2018: Please assign to design committee John 11-12-2018 (on behalf of design committee): For Add Groups function, we need time to discuss in this situation. We will confirm later. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
5 | System management | HKS_High level requirement_20181126.xlsx |  | Add groups | The group name must be unique (is not duplicated). Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
6 | System management | HKS_High level requirement_20181126.xlsx |  | Add groups | The group names should be supported in Vietnamese. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We added. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
7 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The maximum number of characters that can be entered into a "Firstname" and "Lastname" text field are 50 characters. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We accepted and added. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
8 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The maximum length of an account's name are 15 characters. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
9 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The account's name must be unique (is not duplicated). Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
10 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The [email] field needs to be validated before added into the database. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
11 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The [phone number] must be unique (is not duplicated). Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.1.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
12 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The [phone number] field needs to be validated before added into the database. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.1.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
13 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The maximum length of the password is 20 characters and minimun are 6 characters. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.1.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
14 | System management | HKS_High level requirement_20181126.xlsx |  | Add user | The maximum number of user that can be added at the same time are 100 users. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.2.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
15 | System management | HKS_High level requirement_20181126.xlsx |  | Change password | Validate the current password is entered in the User'spassword field is necessary. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.2.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
16 | System management | HKS_High level requirement_20181126.xlsx |  | Change password | The new password must be different than the current password is necessary. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): For Add Groups function, we need time to discuss in this situation. We will confirm later. Hien 11-12-2018 It had been completed. | Complete |  | Thấp | 1.3.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
17 | System management | HKS_High level requirement_20181126.xlsx |  | Change password | The information are entered in the [New Password] text field should be the same as "Confirm password" text field. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
18 | System management | HKS_High level requirement_20181126.xlsx |  | Edit group | On [Edit Group] screen have not yet had [Cancel] button (On AM folder). I assume that it is necessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
19 | System management | HKS_High level requirement_20181126.xlsx |  | Edit group | The maximum number of characters that can be entered into a [Group Name] text field are 50 characters. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
20 | System management | HKS_High level requirement_20181126.xlsx |  | Edit group | The [Group Manager] dropdown list should be sorted in alphabetical order. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We accepted that the "Group Manager" dropdown list must be sorted in alphabetical order. We added this function. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
21 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | The default avatar for each account is necessary. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
22 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | The maximum image upload size is 400 x 400 pixels (varies by device used.) and maximum file size for profile photos is 2MB. It's necsessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
23 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | The dimensions of the [profile picture] will be scaled down to 40 x 40 pixels within the photo feed. It's necsessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
24 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | Uploading a [profile image] function supports JPEG, GIF, and PNG file formats. Profile photos with nudity will be removed. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
25 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | The [email] field can be changed and validated before adding into the database. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We fixed. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
26 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | The [phone number] field needs to be validated before added into the database. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
27 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | The [phone number] must be unique (is not duplicated). Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): For System management screen, we need time to discuss in this situation. We will confirm later. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
28 | System management | HKS_High level requirement_20181126.xlsx |  | Edit user profile | On [Edit profile] screen have not yet had [Cancel] button (On AM folder). I assume that it is necessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
29 | System management | HKS_High level requirement_20181126.xlsx |  | Dashboard | Tooltips would be needed to clarify the meaning of the icon such as [Deleting] icon, [Udating] icon, [Group] icon, [User] icon,..... I assume that it is necessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
30 | System management | HKS_High level requirement_20181126.xlsx |  | Dashboard | Displays the number of users, groups, and roles below each icon / image is nescessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
31 | System management | HKS_High level requirement_20181126.xlsx |  | Dashboard | In this case, the [navigation bar] or [menu] is necessary. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
32 | System management | HKS_High level requirement_20181126.xlsx |  | Move group | On Change Group screen have not yet had [Cancel] button (On AM folder). I assume that it is necessary and will be added. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
33 | System management | HKS_High level requirement_20181126.xlsx |  | Move group | The [Move to] dropdown list needs a default value. Please confirm | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
34 | System management | HKS_High level requirement_20181126.xlsx |  | Move group | The [Move to] dropdown list should be sorted in alphabetical order and current value needs to be disabled in this list. Please confirm | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
35 | System management | HKS_High level requirement_20181126.xlsx |  | Move user | The display of the user's information is transferred to another group is necessary. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
36 | System management | HKS_High level requirement_20181126.xlsx |  | Move user | The [Select group] drop down list needs a default value and should be sorted in alphabetical order. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
37 | System management | HKS_High level requirement_20181126.xlsx |  | Manage Dashboard | The maximum number of records in a page is 10 records. Please confirm. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): We will fix it right now. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan
38 | System management | HKS_High level requirement_20181126.xlsx |  | Manage Dashboard | The user's password must be encrypted. Please confrim. | Nhan 11-12-2018: Please assign to developer team. John 11-12-2018 (on behalf of developer team): For System management screen, we need time to discuss in this situation. We will confirm later. Hien 11-12-2018 It had been completed. | Complete |  | Thấp |  | Hoai Xuan

## Q&A_15130224_TranManhTuong
# | Function area | Document | Doc Version | Section/screen | Comment/Question | Answer | Status | Owner | Priority | Closed In Version | Raised by | Date raised | Required finish date | Date closed
1 | X. Liên lạc | HKS_High level requirement_20181126.xlsx | 0.1 | Form [thông tin liên hệ góp ý] | Need to limit the number of characters entered in the textarea, I think that is necessary and must be added because the user does not enter too long. Please confirm! |  | Hoàn thành |  | Cao | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
2 | X. Liên lạc | HKS_High level requirement_20181126.xlsx | 0.1 | Form [thông tin liên hệ góp ý] | Need to limit the 3 files and <50 mb in the attachment, to reduce the size of the email. Please comfirm! |  | Hoàn thành |  | Cao | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
3 | X. Liên lạc | HKS_High level requirement_20181126.xlsx | 0.1 | Form [thông tin liên hệ góp ý] | When you press the cancel button, the message will be displayed "Bạn có muốn hủy thư?" because it will help the user do not accidentally delete the email. Please confirm! |  | Hoàn thành |  | Cao | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
4 | X. Liên lạc | HKS_High level requirement_20181126.xlsx | 0.1 | Form [thông tin liên hệ góp ý] | Should unify the font because the font is not the same. Please confirm! |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
5 | VIII. Công cụ hỗ trợ thiết kế | HKS_High level requirement_20181126.xlsx | 0.1 | All screen in [Công cụ hỗ trợ thiết kế] | It is important to unify colors for software because it has so many different colors. Please confirm! |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
6 | X. Liên lạc | HKS_High level requirement_20181126.xlsx | 0.1 | Form [thông tin liên hệ góp ý] | Fields marked with * red are mandatory fields. If the user has not logged in, do not enter them. When the submit button is clicked, the system will announce red underneath each required field, and the send command is not executed. I understand that right? Please confirm! |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
7 | VIII. Công cụ hỗ trợ thiết kế | HKS_High level requirement_20181126.xlsx | 0.1 | Cơ cấu bốn khâu bản lề | [Góc bắt đầu] và [góc kết thúc] fields limit the angle of input to too not over 360 deg. I think that right? Please confirm! |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
8 | VIII. Công cụ hỗ trợ thiết kế | HKS_High level requirement_20181126.xlsx | 0.1 | Cơ cấu bốn khâu bản lề | [Góc bắt đầu] field can coincide with the [góc kết thúc] field. I think so? Please confirm! |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
9 | VIII. Công cụ hỗ trợ thiết kế | HKS_High level requirement_20181126.xlsx | 0.1 | All screen in [Công cụ hỗ trợ thiết kế] | When entering all the fields, the button [xuất file3D] and [tải về] need to be enabled? If enabled then the button will be raised. I think so? Please confirm! |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
10 | X. Liên lạc | HKS_High level requirement_20181126.xlsx | 0.1 | Form [thông tin liên hệ góp ý] | When you press the send button, a response will be sent to your email through the customer care staff. I think so? Please confirm |  | Hoàn thành |  | Thấp | 1.0.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
11 | VIII. Công cụ hỗ trợ thiết kế | HKS_High level requirement_20181126.xlsx | 0.1 | Cơ cấu Man | If the [tỷ số truyền] field is negative or divided for 0, when pressing the program button will cause an error. I think so? Please confirm! |  | Hoàn thành |  | Thấp | 1.1.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016
12 | VIII. Công cụ hỗ trợ thiết kế | HKS_High level requirement_20181126.xlsx | 0.1 | Cơ cấu Cam | Need to unify the capitalization of first letter each word because I find them inconsistent. Please confirm! |  | Hoàn thành |  | Thấp | 1.1.1 | Hoai Xuan | 21-10-2016 | 21-10-2016 | 21-10-2016